# Victorian Government Department assessing climate risks impacting assets and services

Department of Energy, Environment and Climate Action is building the climate resilience of public assets and services.

Prepared by DEECA. Please contact climate.action@deeca.vic.gov.au for more information.

# The project

DEECA is responsible for a total of $13.4 billion (DEECA Annual Report 2024-25) in public assets and delivers essential services across its energy, environment, water, agriculture, forestry, resources, climate action and emergency management functions.

DEECA engaged a consultancy to undertake a climate risk assessment of its physical assets and key operational areas. The assessment had two key objectives:

Comprehensive risk identification – identifying risks to DEECA’s assets and other key values, evaluating exposures, vulnerabilities, and potential impacts.

Future-proofing risk management – analysing existing controls, identifying gaps and prioritising risks to inform risk management strategies and guide decision-making.

Over three months, DEECA’s climate risks were assessed in a four-step process aligned with the Commonwealth’s Climate Risk and Opportunity Management Program (CROMP). The CROMP is designed to improve how the public sector manages climate risk.

Scenario analysis and exposure ratings – Climate data was analysed for key hazards across DEECA’s regions, focusing on two future timeframes, 2050 and 2090, and under medium and high emissions scenarios. Exposure ratings for each region were developed based on relative projected change compared to the rest of Victoria.

Mapping DEECA’s assets – Exposure ratings were overlaid with geospatial data of DEECA’s physical assets (e.g. roads, facilities, equipment) to identify where assets are most exposed to future climate hazards.

Data and insights were drawn from the best available Victorian climate science, including from Victoria’s Climate Science Report and the interactive Victoria’s Future Climate Tool (VFCT).

# How climate science was used

Climate exposure varies across Victoria’s regions, resulting in differing impacts to DEECA’s assets, operations, and service delivery. To better understand this variability, scenario analysis was used to provide insight into the overall climate hazard trends affecting DEECA’s assets and values.

Key points & themes

- Department-wide risk assessment

- Scenario and time horizon selection

- User needs

- Public assets and services

Table 1: Time horizons and emission scenario used

| Hazard | Data source | Rationale for selection of data source |
| --- | --- | --- |
| Extreme temperature and heatwave Drought Extreme rainfall and flooding | VFCT (CMIP5) | DEECA’s CMIP5 dataset includes the most recent, available medium emissions scenario (RCP4.5) for Victoria. Note: The most recent CMIP6 dataset for Victoria contains a low emissions scenario (SSP1-2.6) and high emissions scenario (SSP3-7.0). This CMIP6 dataset does not include a medium emissions scenario for which there was preference for in the climate risk assessment. Some emissions trajectories indicate that the low emissions scenario may be breached in the 2030s. As Victoria’s emissions could be higher than the low emissions scenario in the coming decade, the low emissions scenario was not used for the long-term physical risk assessments. |
| Bushfire | Internal | Daily Forest Fire Danger Index (FFDI) projections for Victoria's nine fire regions. The FDDI provides the most up to date and comprehensive fire danger datasets available and has been in operation since 1950. |
| Sea level rise (SLR) and storm surge (Average Recurrence Interval (ARI)) | CSIRO Canute 3.0 | CSIRO Canute 3.0 is the most comprehensive and up-to-date data source for analysing SLR and ARI, available at the time of developing the climate risk assessment. It is well equipped to distinguish between moderate and high emissions scenarios and can provide data for specific coastal locations for 2050 and 2090. |

# The result

As a starting point, Victoria’s Climate Science Report 2024 provided background on observed changes to Victoria’s climate and how these changes are projected to continue.

As the future is uncertain, using different climate scenarios and time horizons allowed DEECA to consider a range of possible longer-term climate changes and their evolution over time.

The availability of this climate data at a local-level also enabled DEECA to better understand climate variability across Victoria’s regions and any potential differing impacts to its assets, operations, and service delivery.

The scenario analysis strengthened DEECA’s ability to better understand the potential scope and context for climate risks, which enables better identification, analysis and prioritisation of risks to DEECA’s assets and values.

The risk assessment identified physical risks across key areas such as emergency preparedness and response capacity, agricultural regulation and support services, staff safety and wellbeing, biodiversity, and public land management.

Risks were assessed using DEECA’s risk management framework. DEECA considered how assets and values could be impacted (positively or negatively) by climate change over time, and the consequences of those impacts.

DEECA prioritised risks with the greatest potential for long-term consequences for detailed analysis and action.

# Publication information

## Acknowledgement of Victorian Traditional Owners

We acknowledge and respect Victorian Traditional Owners as the original custodians of Victoria’s land and waters, their unique ability to care for Country and deep spiritual connection to it.

We honour Elders past and present whose knowledge and wisdom has ensured the continuation of culture and traditional practices.

DEECA is committed to genuinely partnering with Victorian Traditional Owners and Victoria’s Aboriginal community to progress their aspirations.

## Copyright

© The State of Victoria Department of Energy, Environment and Climate Action, June 2026.

## Creative Commons

This work is licensed under a Creative Commons Attribution 4.0 International licence, visit the Creative Commons website (http://creativecommons.org/licenses/by/4.0/).

You are free to re-use the work under that licence, on the condition that you credit the State of Victoria as author. The licence does not apply to any images, photographs or branding, including the Victorian Coat of Arms, and the Victorian Government and Department logos.

ISBN 978-1-76176-818-7 pdf/online/MS word)

## Disclaimer

This publication may be of assistance to you but the State of Victoria and its employees do not guarantee that the publication is without flaw of any kind or is wholly appropriate for your particular purposes and therefore disclaims all liability for any error, loss or other consequence which may arise from you relying on any information in this publication.

## Accessibility

To receive this document in an alternative format, phone the Customer Service Centre on 136 186, email customer.service@delwp.vic.gov.au, or contact National Relay Service on 133 677 or visit http://www.accesshub.gov.au/. Available at DEECA website (www.deeca.vic.gov.au).

End of document.